## Sheet 1
Gantt_Chart_Template (Estimated 60-90 minutes of meetings weekly)
Task | Start Week | Duration (Weeks) | End Week | Assigned To
Identify Stakeholders and Team | 1 | 2 | 2 | Project Manager
Literature Review | 3 | 2 | 4 | Clinical Lead
Define Inclusion Criteria | 4 | 1 | 4 | Clinical Lead
Identify Key Processes | 5 | 1 | 5 | Clinical Lead
Risk Stratification Schema | 6 | 1 | 6 | Clinical Lead
Specify Diagnostics | 7 | 1 | 7 | Clinical Lead
Outline Treatment Options | 8 | 1 | 8 | Clinical Lead
Determine Disposition Criteria | 9 | 1 | 9 | Clinical Lead
Define Monitoring Intervals | 10 | 1 | 10 | Clinical Lead
Finalize Decision Points | 11 | 2 | 12 | Clinical Lead
Define Measures of Success | 13 | 2 | 14 | Clinical Lead
Develop Visual Prototype | 15 | 2 | 16 | Project Manager
Clinical Documentation Integrity Support | 15 | 2 | 16 | Informatics Lead
Usability Testing | 17 | 2 | 18 | Informatics Lead
Patient Education | 15 | 4 | 18 | Informatics Lead
Finalize Pathway & CDS Build | 19 | 2 | 20 | Informatics Lead
Team Approval | 21 | 2 | 22 | Operations Lead
Department Approval | 23 | 2 | 24 | Operations Lead
System Approval | 25 | 4 | 28 | Operations Lead
EHR Integration | 29 | 4 | 32 | IT Lead
EHR Optimization | 33 | 2 | 34 | Informatics Lead
Staff Training & Operationalize Pathway | 35 | 4 | 38 | Operations Lead
Data Analytics | 39 | 8 | 46 | Data Analyst