## Sheet 1
WBS_Template
Task ID | Task Domain | Subtasks | Assigned To | Duration (Weeks)
1 | Project Initiation | Identify stakeholders, define scope, and establish project charter | Project Manager | 2
2 | Pathway Design | Literature review, develop protocols, and define measures of success | Clinical Lead | 13
3 | Usability Testing | Create an AI-augmented visual prototype to beta test | Project Manager | 4
4 | Patient Education | Develop patient education materials | Informatics Lead | 4
5 | Team & System Alignment | Finalize clinical decision support and clinical documentation integrity | Informatics Lead | 10
6 | EHR Integration | Execute functionality, integration, and regression testing | IT Lead | 4
6 | EHR Optimization | Perform end-user acceptance testing | Informatics Lead | 2
7 | EHR Integration | Complete system testing | IT Lead | 2
8 | Staff Training | Develop and implement asynchronous didactics and realtime simulations | Operations Lead | 4
9 | Post-Go Live Evaluation | Analyze data, report trends in process and outcome measures | Data Analyst | 8